## 1. Overview
SecureBin — Closed Testing → Production Test Plan
App | SecureBin (com.websaleem.securebin)
Version | 1.0.4 (versionCode 5)
Track | Google Play Closed Testing
Goal | Meet all Google Play requirements for Production access
Date Created | 12 June 2026
Google Play Production Requirements
Requirement | Target | Status
Minimum opted-in testers | ≥ 12 | ☐ Pending
Testing duration | ≥ 14 consecutive days | ☐ Pending
Tester engagement | Active usage (installs + meaningful sessions) | ☐ Pending
Production questionnaire | Thorough, detailed answers | ☐ Not yet
⚠ IMPORTANT: The 14-day clock starts once you have 12+ testers opted in.
⚠ Testers must ACTIVELY USE the app — simply opting in is not enough.
⚠ Google evaluates engagement and can reject the application if testers are inactive.
⚠ If the production review is rejected, you may need to restart a fresh 14-day cycle.

## 2. Tester Recruitment
Tester Recruitment & Onboarding
Target: 15 testers (minimum 12)
# | Tester Name / Alias | Email (Google Account) | Opted In? | Install Date | Active? | Notes
1 |  |  | ☐ |  | ☐
2 |  |  | ☐ |  | ☐
3 |  |  | ☐ |  | ☐
4 |  |  | ☐ |  | ☐
5 |  |  | ☐ |  | ☐
6 |  |  | ☐ |  | ☐
7 |  |  | ☐ |  | ☐
8 |  |  | ☐ |  | ☐
9 |  |  | ☐ |  | ☐
10 |  |  | ☐ |  | ☐
11 |  |  | ☐ |  | ☐
12 |  |  | ☐ |  | ☐
13 |  |  | ☐ |  | ☐
14 |  |  | ☐ |  | ☐
15 |  |  | ☐ |  | ☐
Onboarding Steps (Send to Each Tester)
1. Join the test: Share the closed testing opt-in link from Google Play Console
2. Install the app from Google Play after opting in
3. Grant camera permission when prompted
4. Complete the setup flow: Select a state and council
5. Scan at least 1 item to confirm the full pipeline works
6. Keep the app installed for the full 14 days
7. Use the app 2–3 times per week
Tester Welcome Message Template
Hi! 👋 Thanks for helping test SecureBin — an AI-powered waste sorting app for Australia. Here's how to get started: 1. Click this link to join the test: [OPT-IN LINK] 2. After joining, install "SecureBin" from Google Play 3. Open the app → select your state & council 4. Point the camera at any waste item and tap the capture button 5. Check which bin it belongs to! Please keep the app installed and use it a few times over the next 2 weeks. Even quick scans of random items around your house help a lot. If anything crashes or looks wrong, please let me know! Thanks 🙏

## 3. Engagement Schedule
14-Day Tester Engagement Schedule
Google evaluates active usage, not just installs. Ask testers to follow this schedule.
Day | Activity | Purpose | Completed?
Day 1 | Install → Setup (state + council) → First scan | Onboarding | ☐
Day 2 | Scan 2 different items | Confirm pipeline | ☐
Day 3 | View scan history | Test history screen | ☐
Day 4 | Scan 1 item from a different bin category | Coverage | ☐
Day 5 | Rest day (app stays installed) | — | ☐
Day 6 | Change council in settings → scan 1 item | Test location update | ☐
Day 7 | Scan 2 items, check history thumbnails | Engagement | ☐
Day 8 | Rest day | — | ☐
Day 9 | Scan 1 item | Engagement | ☐
Day 10 | View 'About' page, check information sources | Feature coverage | ☐
Day 11 | Scan 2 items from different categories | Coverage | ☐
Day 12 | Rest day | — | ☐
Day 13 | Scan 1 item, review full history | Engagement | ☐
Day 14 | Final scan → provide feedback via Google Play | Wrap-up | ☐
Minimum per tester over 14 days: ~10 scans, ~10 app opens

## 4. Setup & First Launch
Test Cases — Setup & First Launch
ID | Test Case | Steps | Expected Result | Pass? | Tester | Notes
S-01 | First launch shows setup | Fresh install → open app | Setup screen appears with 'Welcome to SecureBin' title | ☐
S-02 | All 8 states displayed | View setup screen | ACT, NSW, NT, QLD, SA, TAS, VIC, WA all visible | ☐
S-03 | Select state highlights it | Tap a state (e.g. VIC) | State button turns green, others remain unselected | ☐
S-04 | Council picker opens after state | Select state → tap council field | Modal opens with searchable council list | ☐
S-05 | Council search filters results | Type in search box | List filters to matching councils | ☐
S-06 | Council search — no match | Search for gibberish | 'No councils match' empty state appears | ☐
S-07 | Select council shows tick | Tap a council | Council is highlighted with ✓, picker closes | ☐
S-08 | Continue disabled without selections | Open setup with no state/council | 'Continue' button is greyed out / disabled | ☐
S-09 | Continue enabled with selections | Select state + council | 'Continue' button is green and tappable | ☐
S-10 | Setup completes → camera screen | Select state + council → tap Continue | Navigates to camera screen | ☐
S-11 | Disclaimer text is visible | View setup screen | 'Independent app' disclaimer box with link is displayed | ☐
S-12 | 'View information sources' link works | Tap the link in disclaimer | Navigates to About screen | ☐

## 5. Camera & Scanning
Test Cases — Camera & Scanning
ID | Test Case | Steps | Expected Result | Pass? | Tester | Notes
C-01 | Camera permission requested | Open camera screen (first time) | Android permission dialog appears | ☐
C-02 | Camera preview loads | Grant permission | Live camera preview fills the screen | ☐
C-03 | Capture button visible | View camera screen | Capture button and reticle overlay visible | ☐
C-04 | Capture a photo | Point at item → tap capture | Image is captured, loading/processing state shown | ☐
C-05 | Image cropped to reticle | Capture an image | Only content within the 4:3 reticle frame is sent | ☐
C-06 | Processing indicator shown | After capture | Loading spinner or progress indicator visible | ☐
C-07 | Result appears after processing | Wait for Bedrock response | Result screen displays with bin colour + item name | ☐
C-08 | Settings button accessible | View camera screen | Settings/gear icon is visible and tappable | ☐
C-09 | Settings opens location update | Tap settings | Setup screen opens in 'Update Location' mode with Cancel button | ☐
C-10 | Camera permission denied | Deny camera permission | Appropriate error/guidance message shown | ☐

## 6. Result Screen
Test Cases — Result Screen
ID | Test Case | Steps | Expected Result | Pass? | Tester | Notes
R-01 | Bin colour card displayed | Complete a scan | Coloured bin card shows correct bin colour | ☐
R-02 | Item name displayed | Complete a scan | Identified item name is shown (e.g. 'Plastic Bottle') | ☐
R-03 | Reason / explanation shown | Complete a scan | Text explaining why this bin was chosen | ☐
R-04 | Navigate back to camera | Tap back / scan again | Returns to camera screen ready for next scan | ☐
R-05 | Result saved to history | Complete a scan → go to history | New scan appears in history list | ☐

## 7. Scan History
Test Cases — Scan History
ID | Test Case | Steps | Expected Result | Pass? | Tester | Notes
H-01 | History screen accessible | Tap history icon/button | History screen loads | ☐
H-02 | Empty history state | Fresh install → open history | 'No scans yet' or similar empty state | ☐
H-03 | Scans listed chronologically | Perform multiple scans → open history | Most recent scan at top | ☐
H-04 | History item shows details | View history list | Each item shows thumbnail, item name, bin, timestamp | ☐
H-05 | Clear all history works | Tap 'Clear All History' | All scans removed, empty state shown | ☐
H-06 | History persists across restarts | Perform scan → close app → reopen → check history | Previous scans still present | ☐

## 8. About & Location
Test Cases — About Screen
ID | Test Case | Steps | Expected Result | Pass? | Tester | Notes
A-01 | About screen loads | Navigate to About | About page with app information renders | ☐
A-02 | Information sources listed | View About screen | Data source references are visible | ☐
A-03 | Back navigation works | Tap back from About | Returns to previous screen | ☐
Test Cases — Location Update
ID | Test Case | Steps | Expected Result | Pass? | Tester | Notes
L-01 | Update location from camera | Tap settings on camera screen | Setup screen in update mode with current selections pre-filled | ☐
L-02 | Change state clears council | Select new state | Council resets to 'Select your council…' | ☐
L-03 | Save updated location | Change state + council → Save | Returns to camera, next scan uses new location | ☐
L-04 | Cancel update preserves original | Open update → tap Cancel | Returns to camera with original location unchanged | ☐
L-05 | Location persists across restarts | Update location → close app → reopen → check settings | Updated location is retained | ☐

## 9. Bin Coverage
Bin Category Coverage Testing
Scan items to verify AI accuracy across all bin categories
ID | Item to Scan | Expected Bin | Actual Bin | Correct? | Council Used | Notes
B-01 | Dirty food wrapper | 🔴 Red (General Waste) |  | ☐
B-02 | Empty plastic bottle | 🟡 Yellow (Mixed Recycling) |  | ☐
B-03 | Banana peel / apple core | 🟢 Green (Organics / FOGO) |  | ☐
B-04 | Glass jar | ⚪ White or 🟡 Yellow (Glass/Recycling) |  | ☐
B-05 | Old battery | 🔵 Blue (Drop-Off Required) |  | ☐
B-06 | Old t-shirt | 🟠 Orange (Reuse / Donate) |  | ☐
B-07 | Cardboard box | 🟡 Yellow (Mixed Recycling) |  | ☐
B-08 | Used paper towel | 🟢 Green (Organics / FOGO) |  | ☐
B-09 | Broken ceramic mug | 🔴 Red (General Waste) |  | ☐
B-10 | Empty aluminium can | 🟡 Yellow (Mixed Recycling) |  | ☐

## 10. Edge Cases
Test Cases — Edge Cases & Error Handling
ID | Test Case | Steps | Expected Result | Pass? | Tester | Notes
E-01 | No internet connection | Turn off Wi-Fi/data → scan | Graceful error message, no crash | ☐
E-02 | Scan non-waste item | Point camera at face / wall / sky | Returns 'Unsure / Ask Council' (grey) or sensible response | ☐
E-03 | Rapid multiple captures | Tap capture button rapidly | App handles gracefully, no duplicate scans or crashes | ☐
E-04 | Low light conditions | Scan in dim room | App either captures or shows guidance, no crash | ☐
E-05 | App backgrounded during processing | Start scan → switch to another app → return | Result still appears or app recovers gracefully | ☐
E-06 | Large scan history | Accumulate 20+ scans | History screen scrolls smoothly, no lag | ☐
E-07 | Backend timeout | (If possible) Wait for timeout | Error message shown, option to retry | ☐
E-08 | Screen rotation locked | Rotate device | App stays in portrait mode (as configured) | ☐

## 11. Device Compatibility
Device Compatibility Testing
Minimum SDK: 24 (Android 7.0 Nougat). Test on a variety of devices.
# | Device Model | Android Version | Screen Size | All Tests Pass? | Tester | Notes
1 |  |  |  | ☐
2 |  |  |  | ☐
3 |  |  |  | ☐
4 |  |  |  | ☐
5 |  |  |  | ☐
6 |  |  |  | ☐
7 |  |  |  | ☐
8 |  |  |  | ☐
9 |  |  |  | ☐
10 |  |  |  | ☐

## 12. Backend API
Backend & API Verification
Run using test/testbin.py
ID | Test | Command | Expected | Pass? | Notes
API-01 | Basic scan (no location) | python test/testbin.py test/images/plastic_bottle.jpg --base-url $URL | Returns bin + item + reason + confidence | ☐
API-02 | Scan with VIC council | python test/testbin.py test/images/banana_peel.jpg --base-url $URL --state VIC --council "City of Melbourne" | Returns council-specific advice | ☐
API-03 | Scan with NSW council | python test/testbin.py test/images/plastic_bottle.jpg --base-url $URL --state NSW --council "City of Sydney Council" | Returns council-specific advice | ☐
API-04 | All test images | Run testbin.py for each image in test/images/ | All return valid results | ☐
API-05 | Invalid media type | Send non-JPEG to presign | Error response, no crash | ☐
API-06 | Invalid jobId | GET /result/invalid-uuid | Error response with appropriate status | ☐

## 13. Questionnaire Prep
Production Questionnaire Preparation
Thorough answers significantly increase approval chances. Prepare in advance.
Question Area | Suggested Answer Points | Your Draft Answer
What does your app do? | SecureBin uses AI (Amazon Bedrock) to classify waste items via the device camera and tells users which bin to use, tailored to their Australian state and council. No login required.
How did you test? | 15 testers across multiple Australian states, testing over 14+ days. Testers followed a structured engagement schedule covering all features.
What feedback did you receive? | Document actual feedback: bugs found & fixed, UI improvements, accuracy feedback on bin classifications.
What devices were tested? | List actual devices and Android versions tested (aim for 3+ unique devices).
How did you address issues? | Describe any bugs fixed during testing, version updates pushed to testers.
Target audience | Australian residents who want to sort waste correctly according to their local council's rules.
Content rating | No violence, no user-generated content, no ads, no in-app purchases. Camera used only for waste classification.

## 14. Timeline
Project Timeline
Date / Day | Milestone | Status | Notes
Day 0 (Today) | Finalize tester list, send opt-in invitations | ☐
Day 1–2 | All 15 testers opted in & app installed | ☐
Day 2 | Confirm 12+ testers active → 14-day clock starts | ☐
Day 3–7 | Testers follow engagement schedule (Phase 1) | ☐
Day 7 | Mid-point check: verify 12+ still active, review feedback | ☐
Day 8–14 | Continue engagement schedule (Phase 2) | ☐
Day 14 | Run all backend API tests, compile device compatibility results | ☐
Day 15 | Collect final feedback from testers | ☐
Day 16 | Complete production questionnaire, review all test results | ☐
Day 16 | APPLY FOR PRODUCTION ACCESS | ☐

## 15. Pre-Submit Checklist
Pre-Submission Checklist
Confirm ALL items before applying for production
# | Checklist Item | Done? | Notes
1 | 12+ testers have been opted-in for ≥14 consecutive days | ☐
2 | Testers have actively used the app (multiple sessions, not just install) | ☐
3 | All Setup/First Launch tests (S-01 to S-12) pass | ☐
4 | All Camera & Scanning tests (C-01 to C-10) pass | ☐
5 | All Result Screen tests (R-01 to R-05) pass | ☐
6 | All History tests (H-01 to H-06) pass | ☐
7 | All About Screen tests (A-01 to A-03) pass | ☐
8 | All Location Update tests (L-01 to L-05) pass | ☐
9 | Bin category coverage tested (B-01 to B-10) with reasonable accuracy | ☐
10 | Edge cases tested (E-01 to E-08) — no crashes | ☐
11 | Backend API tests pass (API-01 to API-06) | ☐
12 | Tested on 3+ unique Android devices across different OS versions | ☐
13 | No critical bugs remain open | ☐
14 | App Store listing is complete (description, screenshots, privacy policy) | ☐
15 | Production questionnaire answers are prepared with detailed responses | ☐
16 | Content rating questionnaire is completed in Play Console | ☐
17 | Data safety section is filled out (camera permission, no data collection requiring login) | ☐
18 | Privacy policy URL is set in Play Console | ☐

## 16. Bug Tracking
Bug Tracking
Severity: 🔴 Critical (crash/data loss) · 🟡 Major (feature broken) · 🟢 Minor (cosmetic/UX)
# | Date | Tester | Description | Screen / Feature | Severity | Status | Fixed in Version | Notes
1 | [5 empty] | ☐ Open
2 | [5 empty] | ☐ Open
3 | [5 empty] | ☐ Open
4 | [5 empty] | ☐ Open
5 | [5 empty] | ☐ Open
6 | [5 empty] | ☐ Open
7 | [5 empty] | ☐ Open
8 | [5 empty] | ☐ Open
9 | [5 empty] | ☐ Open
10 | [5 empty] | ☐ Open
11 | [5 empty] | ☐ Open
12 | [5 empty] | ☐ Open
13 | [5 empty] | ☐ Open
14 | [5 empty] | ☐ Open
15 | [5 empty] | ☐ Open
16 | [5 empty] | ☐ Open
17 | [5 empty] | ☐ Open
18 | [5 empty] | ☐ Open
19 | [5 empty] | ☐ Open
20 | [5 empty] | ☐ Open